## Sheet1
Goal | Subtask | Owner | Due Date | Status | Depends On | Notes
Pixel-to-Meter Conversion | Find known meter lengths for visual data. Track in metadata file. | Jonathan | 10/30 | Planned | -
Pixel-to-Meter Conversion | Implement pixel-to-meter feature using reference line |  | 10/31 |  | Validate pixel ratio using reference line
Pixel-to-Meter Conversion | Verify consistency across resolution and different source videos. |  | 11/01 |  | Test across multiple resolutions
Deformation Testing Framework | Define fixed-time and delta time categories. Report in notes and in TPS |  | 11/02 |  | -
Deformation Testing Framework | Adhere to testing plan and/or update testing plan |  | 11/04 |  | Define fixed-time and delta-t test categories
Deformation Testing Framework | Record deformation results in test table |  | 11/06 |  | Establish pass/fail accuracy criteria
Velocity Module Development |  |  | 11/05 |  | Verify consistency across datasets
Velocity Module Development | Implement basic Δx/Δt function |  | 11/07 |  | Draft displacement → velocity workflow
Velocity Module Development | Validate velocity results with sample data |  | 11/10 |  | Implement basic Δx/Δt function
Velocity Module Development | Integrate velocity with deformation tracking |  | 11/12 |  | Validate velocity results with sample data
Task Organization | Combine all TPS and project files into one shared folder |  | 10/29
Task Organization | Upload to Copilot to extract subtasks and dependencies |  | 10/30 |  | Combine all TPS and project files into one shared folder