# Team Progress Summary

Week: 10

Participating Group Members:

John Ahn, Jonathan Kim

Submission Date: 11/13/25

# Group Member Timecards

All instructions and sample information should be deleted before submission

## Group Member (John A)

| Week | Date | Start Time | End Time | Total Time | Task | Completion Status |
| --- | --- | --- | --- | --- | --- | --- |
| 3 | 11/11/25 | 1:00 | 2:15 | 1:15 | Create TPS Start finals prep - Start slides | 100% |
| 3 | 11/13/25 | 1:00 | 2:15 | 1:15 | Take notes during advisor meeting Complete TPS | 100% |
|  |  |  |  |  | Work on the slides | 20% |

## Group Member 2(Jonathan K)

| Week | Date | Start Time | End Time | Total Time | Task | Completion Status |
| --- | --- | --- | --- | --- | --- | --- |
| 3 | 11/11/25 | 1:00 | 2:15 | 1:15 | Start preparations for the final demo and practice final demo. | 100% |
|  | 11/13/25 | 1:00 | 2:15 | 1:15 | Attempt to create an automated cell boundary system. Computer vision is not at the level where it can accurately detect the cells with contrast. | 100% |

## Group Member 3(Replace with Name)

| Week | Date | Start Time | End Time | Total Time | Task | Completion Status |
| --- | --- | --- | --- | --- | --- | --- |
| 3 |  |  |  |  |  |  |

# Progress Summary

## Planned Goals and Accomplishments

This week’s main goal is still getting ready for final presentations coming up after break.

Another goal we came up with (with our advisor) was getting a constant time running in the MATLAB script / our program. This is because each individual frame is not recorded at a constant time.

Accomplishments:

We have completed a two-frame analysis feature, the length of the cell in the x and y direction, as well as pixels to nanometers conversion.

We learned our limitations (listed in the barriers sections) given the amount of time left during this semester. It’s listed as an accomplishment because it allowed us to turn our focus to something more doable given our circumstances.

## Barriers to the Project

We tried getting computer edge detection to work but weren’t able to do so. This could be due to either the lack of tools that MATLAB provides or our lack of experience with the language. In addition, there is not an ample amount of time in the rest of the semester to troubleshoot the edge detections.

A lack of communication with one of the members still continues to be a problem this week.

## Next Weeks Goals

We are shifting goals from trying to accomplish automated cell edge detection towards something more feasible like a constant time.

Once a constant time is established, it will allow for possible velocity measurements in the future.

We’re continuing to work on the slides for our final demo.

For next week, we will continue to work on the slides and get a recording of our code working.

# Advisor Meeting Notes

Very quick meeting:

11/13/2025

New goals:

Get a constant time

Velocity will also be easy if we're able to get the time

This will definitely more doable than trying to get cell detection

## Learning Objectives and Rubric for Assignment

- Students will be able to effectively plan for completing a long-term project

- Students will be able to reflect on how their contributions affect the group project as a whole

- Students will be able to identify barriers to success and find the resources to overcome them

ABET SO: 5, 7A, 7B

| Criteria | Mastery | Satisfactory | Room for Improvement | ABET | L.O |
| --- | --- | --- | --- | --- | --- |
| Group member timecards (10pt) | Note: this can be graded student-to-student, please adjust each student’s grade individually Student has completed their timecard for the week with detailed descriptions of what tasks they worked on. They have noted the completion status of the task and how much time was spent on the task. | The student’s timecard is incomplete or otherwise vague in describing the tasks. | Not completed or they wildly overestimated the time they spent on a task or did not describe the task. | 5 | 1,2 |
| Planned goals (10pt) | Students effectively discuss what goals they planned to have completed this week and whether those goals were met. They reference their gantt chart/project management system. Each group member has goals they discuss. | Students discuss their goals, but it is evident they adjusted their goals without discussing why or otherwise are vague in their accomplishment description. | Missing or extremely vague. Student’s don’t have goals they are championing. | 5 | 1,2 |
| Barriers (5pt) | Students are able to discuss barriers to their project success, including the reasons why certain goals may not have been accomplished this week. They also identify the resources they need to move past these barriers. | Students are vague in their description of barriers or have minimal understanding of the resources they need. | Students cannot identify any resources they need or seem to only have external/vague barriers. | 5,7a,7b | 3 |
| Next Week Goals (5pt) | Students reference their gantt chart/project management software and clearly lay out their goals for the next week, assigning a champion to each one. | Student’s are vague or don’t reference their project management system. | Student’s are extremely vague in discussing goals and do not assign champions to each one. | 5 | 1 |
| Advisor Meeting Notes (5pt) | Students have taken notes during their weekly meeting with their advisor and those notes are clear and detailed. | There are notes, but they are vague. | No notes or otherwise insufficient. | 5 | 1 |
| Discretionary (5pt) | These are points are for any other aspect of the report that the advisor would like to comment on. This is at the discretion of the advisor. |  |  |  |  |

40points