# Team Progress Summary

Week: 4

Participating Group Members:

John Ahn

Jonathan Kim

Demetrius Schank

Submission Date: 9/18/2025

# Group Member Timecards

All instructions and sample information should be deleted before submission

## Group Member (John Ahn)

| Week | Date | Start Time | End Time | Total Time | Task | Completion Status |
| --- | --- | --- | --- | --- | --- | --- |
| 4 | 9/16/25 | 1:00 | 2:15 | 1:15 | Tried getting Matlab code to work with the avi files | 50% |
|  | 9/18/25 | 1:00 | 2:15 | 1:15 | Take advisor notes Find some metadata on the video files found and the ones we plan on using | 70% |

## Group Member 2(Jonathan Kim)

| Week | Date | Start Time | End Time | Total Time | Task | Completion Status |
| --- | --- | --- | --- | --- | --- | --- |
| 4 | 9/16/25 | 1:00 | 2:15 | 1:15 | Troubleshooting MATLAB, figured out it is slightly inconsistent. | 60% |
|  | 9/18/25 | 1:00 | 2:15 | 1:15 | Met with advisor, find out data about videos to use in calculations, (e.g. speed of video, cell diameter/volume, z-length of channel) | 80% |

## Group Member 3 (Demetrius Schank)

| Week | Date | Start Time | End Time | Total Time | Task | Completion Status |
| --- | --- | --- | --- | --- | --- | --- |
| 4 | 9/16/25 | 1:00 | 2:15 | 1:15 | Looked for additional video content publications regarding red blood cells through capillaries. Nothing concrete found, but looking through articles and their references for video sources. Signed up for Dr. K meeting for midterm prep. | 90% |
|  | 9/18/25 | 12:40 | 12:55 | 0:15 | Looked for more video material of red blood cells. Set up folder in onedrive specifically meant for the gathered videos and its data (its sources, metadata, etc). | 100% Videos 0% Metadata |
|  |  | 1:00 | 1:30 | 0:30 | Meeting with Dr. Wynne. Notes in advisor meeting notes section, taken by John Ahn. Shared folder to Dr. Wynne and J of our project. | 100% Meeting |
|  |  | 1:35 | 2:15 | 0:40 | Further compiled documents in excel file, worked on TPS, started organizing metadata file for our own tracking. |  |
|  |  | 6:55 | 7:20 | 0:25 | Finished and submitted TSP | 100% |

# Progress Summary

## Planned Goals and Accomplishments

Accomplishments:

Found blood cells videos and some metadata

Demetrius:

Researched NIH, National academy, and Lab on chip try find a few select microfluidic video files that clearly show a red blood cell changing shape through a capillary. Found such and put it in our group folder labeled RBC videos.

John and Jonathan:

Troubleshoot last year’s project, determined that there are too many non-working elements that are preventing us from adding to this project. Instead, we will develop a tool for ourselves, not tracking the same data as the previous year group. Further continuation of this project will marry the two projects together.

Goals:

Demetrius and John: Find the history of the video files (2 videos) / quality of the things shown in the video. Look for more libraries.

Jonathan: Get MATLAB code running. Doesn't have to be too accurate but have something to show Dr. Klein next week during the afternoon meeting about upcoming demos.

Demetrius Goals:
	With the creation of new documents, my goals by next week are to ensure that new documents are organized. Our 9/18 work time was generally productive, but I still feel that our roles have been confusing. We’d say some people would work on one project, but then switch gears. I want to make sure that COMMUNICATION in the team is going to be smoother in the future. I want to have the metadata file finished in time during or before our Tuesday meeting, given personal time grants such. Having such assignment done before the Tuesday meeting will enable a faster timeline for the project.
	Another goal I have is to update the Gantt chart to reflect the project goals further. This will be updated in time for next week’s TPS report, hopefully done before next week’s first meeting as well. This will make it so the team has a better idea of their tasks AND so that we can refer to the gannt chart in later TPS reports.

Group: prepare for meeting with Dr. Klein, and also have something to show Dr. Wynn. Both are next thursday, the latter being at 1:00 and the former is 2:00 – 2:15.

## Barriers to the Project

John A: I tried getting the matlab code to run with the avi files that J provided, but kept getting errors. However, other group members claimed it worked last time, so maybe its just a Mac thing (where it doesnt work): solution was to convert the avi files in mp4 files. But now i had to download an extension which is still not working

I also tried looking for some history of the videos we found but found very little to  no info about it. We had to do some caluclations by ourselves

Jonathan K: Anticipated barriers, when finding cell shape and any possible deformations after it goes through a capillary, the area could decrease just because it rotated (in 3D), this could lead to some inaccuracies.

Demetrius: As Dr. Wynne explained, there are few microfluidic microscopy videos imaging cells through capillaries; many sources I found were simulations of such. Finding a video that clearly demonstrates what the team was looking for (relatively 2D RBC moving through capillary and/or changing shape through capillary) took longer than expected.

# Advisor Meeting Notes

9/18/2025

Update: found journal site

Compile library – lab on chip

Microfluidics

Pretty hard to find bc no one does this lol

Video is big channel: we tryna focus on small channels bc small cells

Focus on: squeezing aspect and how shape changes

Quality of cells during deformation

What percent of cell is changing on x-y-z

Which method we tryna do?

Cells create oblong (tear drop) shape

If we can measure the shape has changed so we can measure in x and y directions

Z would be tough

Cross section of area, and see how the area changes

May be some tool out there that allows aproximations

Don’t know which one would be good to ctach deformation

Predict channel

How much deformation occurred

Limited by diameter

Expansion or contractions

Q: is change consistent across all cells

Would be really good if yes

But if not, if different shapes go through different changes in same channels

Demonstrate our code working

Units of time for the videos

Next group: try to implement it to all

Maybe:

Different characteristics and maybe next year combines the two (last and this year)

Dr. Wynne rec: find a template for image processing video for:

Finding area, tracking movement, changing shape

Use the two videos we already have: very unique

Have code that can go between the two videos

Two different cell shape

Better than having code that doesn’t work across 100 videos lol

Can use the videos already have (the one that doesn’t change shape just slides) as control

No deformation is seen with our eyes, so if code picks up deformation then the code needs some fixing

Cells squeezing through capillaries

Shape thingy is not too well known bc it's very recent

Tools to leap frog off of, or just create our own bc its new

Next week: have two videos, find the history (people gon think we made it up)

Its real, people just havent digged into it yet

Speed of videos, (data) size of channels, materials of cells, materials of channels,

Try learning: Letech, overleaf

Published matlab scrips, bibliographic of data videos

Makes sure everything goes in the oneDrive