# Team Progress Summary

Week: 5

Participating Group Members:

John A

Jonathan K

Demetrius S

Submission Date: Sept 25, 2025

# Group Member Timecards

All instructions and sample information should be deleted before submission

## Group Member (John A)

| Week | Date | Start Time | End Time | Total Time | Task | Completion Status |
| --- | --- | --- | --- | --- | --- | --- |
| 5 | 9/23 | 1:00 | 2:15 | 1:15 | Meetup with group virtually Tested the code |  |
|  | 9/25 | 1:00 | 2:15 | 1:15 | Take notes during meetings with Dr. Wynne and Dr. Klein | 100 |

## Group Member 2(Jonathan K)

| Week | Date | Start Time | End Time | Total Time | Task | Completion Status |
| --- | --- | --- | --- | --- | --- | --- |
| 5 | 9/23/25 | 1:00 PM | 2:15 PM | 1:15 | Met up virtually, tested MATLAB code, and gave suggestions. | 100% |
|  | 9/25/25 | 1:00 PM | 2:15 PM | 1:15 | Spoke with advisor to see what factors to work on next, velocity and deformation rate. Mid-term demo prep meeting. | 100% |

## Group Member 3(Demetrius Schank)

| Week | Date | Start Time | End Time | Total Time | Task | Completion Status |
| --- | --- | --- | --- | --- | --- | --- |
| 5 | 9/23/25 | 1:00 PM | 2:15 PM | 1:15 | Reviewed and tested code written by jonathan, suggested some possible improvements to make. Searched more for supplemental video metadata/began formatting the already existing data. | 30% |
|  | 9/25/25 | 10:50 AM | 11:35 AM | 0:45 | Searched for more video metadata and experiement metadata for the primary video source we are using (c3lc50427a.wmv). | 40% |
|  |  | 12:40 PM | 12:55 PM | 0:15 | continued formatting metadata for our records. For video (c3lc50427a.wmv). | 45% |
|  |  | 1:00 PM | 2:10 PM | 1:10 | Meeting with Dr. Wynne, demonstrating code and going over which specific modifications. This includes going over the frame-rate/time problem, reported vs. playback resolution issue, and pixel to irl measurement issue. Worked a little bit more on gathering necessary metadata for our project for the "c3lc50427a.wmv" video. Had midterm demo meeting with Dr. Klein. Discussed plans to finish TPS 5, instituting a flexible deadline of 8pm on the 25th to finish tps descriptions. Briefly discussed goals for next week during the Dr. Klein meetings, which, broadly, is to get everyone up to speed on how our code works for our midterm presentation in two weeks. | 55% |
|  |  | 4:50 PM | 6:00 PM | 1:10 | Worked on my portion of the TSP report. Finished fathering metadata for the video. Email advisor Wynne to schedule midterm demo. | 65% |
|  |  | 9:45 PM | 11:57 PM | 2:12 | Finished TPS report. Specified more of our next week goals, future goals, and accomplishments to include details of when and where deliverables will finished. Touched up all categories of the progress report besides member timesheets and advisor notes. | 100% |

# Progress Summary

## Planned Goals and Accomplishments

Accomplishments:

There is now a foundation to build upon, now it is just seeing how many different factors can be calculated and added to this foundation.

MATLAB code can calculate the area of a hand drawn region in units of pixels, as well as the change in x and y between two different hand drawn regions.

Demetrius Accomplishments/Completed Plan Goals:

Based on what John and/or Jonathan had started gathering for the metadata, I finished gathering all (reasonably) relevant video metadata and experiment conditions metadata for the video titled "c3lc50427a.wmv". That was finished 9/25 between my 4:50- 6:00 PM work time; however, it was mostly gathered during my 9/25 10:50-11:35AM. This was before our weekly advisor meeting, and well equipped me to talk about the barriers to our project. This data can be found in the “… Fall 2025 > RBC Movies > ‘Video Metadata.docx’ ”  If desired, the article that is associated to can be found in “…Fall 2025 > RBC Movies > ‘Article PDFs’ ”. You may need to locate the “Legend – Video PDF Sources.xlsx” file in the aforementioned “RBC Movies” folder to find out which articles correspond to which videos.

On that note, I furthered my overall goal of organizing our files. Its been done mostly along the way, ie. No specific time/meeting, but the “Legend…” file mentioned above is an example of organization attempts being made. I created the “Article PDFs” folder, and I also moved the “MATLAB Scripts” folder out from the “RBC Videos” folder, as I didn’t see why it would make sense to have that folder in there. Perhaps going forward, I will make better note of that.

## Barriers to the Project

First off, it is impossible for our group to get any video data of the z-axis direction of the videos we find. Since all of these cells exist in 3D space, and we are working with 2D video, there will always be a possible third dimension that could affect our deformation calculations. This is something that we simply must acknowledge as an unavoidable constraint for our project. To circumvent this, the videos we have seemingly don’t rotate the cell in the Z direction.

Furthermore, video compression has posed another challenge for the group. Possibly due to the video being uploaded online, the video frame rate and resolution are not what the margins of the video report. For example, in the “Video Metadata.docx” file, we have data showing that there are only 389 unique frames in the sample video we have, at a reported 3000fps, despite there being over 1000+ frames in the video. This means that there are duplicate videos. This does not pose a challenge to our current iteration of our code, since we are not yet measuring time passed from frame A to frame B. However, if this is an issue, we would either a) need to edit the video and remove all duplicated frames or b) write MATLAB software to detect unique frames and discard any duplicated frames to use when analyzing the video.

On another note, Demetrius did not get to working on the Gannt chart as he had hoped. This is in part due to his schedule and lack of definition. He never wrote a definitive date on paper—other than on his own calendar—so it was always towards the bottom of my priorities for this project/my schedule. Going forward, any goals I want to complete will have definitive dates on when I want to get them done by, which is what I should have done all along.

## Next Weeks Goals

Seeing that Midterm demos are in 12-14 days, our primary goal is to ensure that everyone is prepared for that demo. To do this, the group must go through each part of our MATLAB code to ensure we all have a grasp of each process. Although we have comments in the code, we expect to add more detailed comments to help with everyone’s comprehension. Again, we have a document explaining the purpose, location, functionality, key components, and user interface of the code, but would still need to tailor it to each member so that we all. By the end of day Tuesday, September 30th, each member will have their own version of notes of how the most recent version of the MATLAB code is. This is the version that will be demonstrated at the Midterm Demo regardless of if changes or improvements are made to the code after that point. These will be placed in the “Cell Imaging > Fall 2025 > MATLAB Scripts > Member Notes” directory, with a file titled ‘README_memberNotes.txt” listing the title/version of the code we are working with.

Looking at the Midterm Demo Rubric, there are a few things that we must deliberate further. First, we must revisit the ‘technical standard’ we found last semester and relate it to our project. If we can’t relate it to our project, we must find another standard more relevant to our design. This will be a focus as soon as the group finishes the previous ‘note taking’ task. It is expected that this task will be done by end-of-day Thursday, September 2nd. The current ‘technical standard’ we have for this project is listed in within our “Cell Imaging > Spring 2025” folder, most likely listed among our references in one of our blackboard deliverables. It is currently unknown where the new technical standard will be recorded and what files will be needed for this, and will likely be included in next week’s TPS in ‘achievements’.

Lastly, the group also must finalize deciding when our Midterm Demos will be. Spearheaded by Demetrius, it is already determined that Dr. Wynne is unavailable for all remaining time slots. Lets see if it is possible to organize another time, and if not, chose the best time for all members of the group excluding our advisor Dr. Wynne. An email will be sent to Dr. Klein regarding this issue before the groups 9/30 meeting to get a response in time to share for the meeting.

Other indeterminate Goals:

Here is a list of other goals that are on our radar, but are not necessarily required to be completed by next week:

- A method to scale the pixels measurements to real-life measurements. Going to be done with drawing a line, then defining the length of the line. This line then acts as a scale for a pixel to meter ratio.

- Create different scripts for additional features, ie velocity, ‘unique frame detection’ script, etc (should be listed in Meeting Notes from John).

- Further update Gantt Chart, especially given the “list of doable things” and “List of perfect world” tasks.  –  Demetrius

- Create “Fall 2025” Folder legend, detailing exactly what each file/folder is in the Fall 2025 Folder. – Demetrius

- (This is ideal world with excess extra time) Go back and create legend for “Spring 2025” Folder, explaining each file and document in that folder. This will be difficult due to the time that has passed and the overall disorganization of the folder, as there are files from previous iterations of this project in that folder.

# Advisor Meeting Notes

When you share this report with your advisor at your weekly meeting, take notes and record them here.

9/25/25

We showed Dr. Wynne our demo / working code that we got

- try to get it working with videos rather than between two frames

Obv very difficult to do

So trying to get it accurate

What is the best way to measure the cells

What about

Paper reported that this cell size has this particular dimension

Create legend in own script

Have fixed dimensions and scale / calculate

Issues with compression / stretching / different sizes

Make matlab find a visual artifact

For this image, the length is this

Draw line, make matlab read video

"This channel is 10micro-m" make matlab scale everything else relative to that

Pixel to micrometer ratio?

She would like to see:

The measurements, create a scale based on whats known

Shows power of pixel based – real dimensions

Can see cases where our pixel based is flawed

Issues:

Duplicate frames

Cant trust video with time bc not linear

Can make matlab count time differently

Ie: count this many frames and make that 1 time period

Is it possible for matlab to get those frames

Maybe make new time scale? For demo purposes

Our goal:

Take this tool and apply to videos

Not really figuring out what someone else's videos are presenting

Cleanup:

Suitable for time issues

Velocity counting

List of doable of things:

Two channels ✅

Code that’s running that will estimate shape ✅

Determine area – for now it did it in pixels

Update pixels to measurements

Time / rate of velocity / rate of deformation

Make deformation faster than normal cells

List of perfect world: (everything works first time go)

Taking video from any source

Finding true time of those cell transforms

Deformation rate in the z direction (this PERFECT perfect world lol)

Big picture

Synthetic bio – custom cells as indivual

Change dna to make it do something in response to some stimulus

Imagine we had one, that went through channel and change shape based on what it detected

Gives sense of size of shape

Channel is controlled

Whole cell sensor and monitors

Engineering:

What tools are we using? Matlab

What frames are unique

List of deliverables:

Areas to measurements – pixels to meters

Quantifiable things

    - Are we giving code, tables, etc

## Learning Objectives and Rubric for Assignment

- Students will be able to effectively plan for completing a long-term project

- Students will be able to reflect on how their contributions affect the group project as a whole

- Students will be able to identify barriers to success and find the resources to overcome them

ABET SO: 5, 7A, 7B

| Criteria | Mastery | Satisfactory | Room for Improvement | ABET | L.O |
| --- | --- | --- | --- | --- | --- |
| Group member timecards (10pt) | Note: this can be graded student-to-student, please adjust each student’s grade individually Student has completed their timecard for the week with detailed descriptions of what tasks they worked on. They have noted the completion status of the task and how much time was spent on the task. | The student’s timecard is incomplete or otherwise vague in describing the tasks. | Not completed or they wildly overestimated the time they spent on a task or did not describe the task. | 5 | 1,2 |
| Planned goals (10pt) | Students effectively discuss what goals they planned to have completed this week and whether those goals were met. They reference their gantt chart/project management system. Each group member has goals they discuss. | Students discuss their goals, but it is evident they adjusted their goals without discussing why or otherwise are vague in their accomplishment description. | Missing or extremely vague. Student’s don’t have goals they are championing. | 5 | 1,2 |
| Barriers (5pt) | Students are able to discuss barriers to their project success, including the reasons why certain goals may not have been accomplished this week. They also identify the resources they need to move past these barriers. | Students are vague in their description of barriers or have minimal understanding of the resources they need. | Students cannot identify any resources they need or seem to only have external/vague barriers. | 5,7a,7b | 3 |
| Next Week Goals (5pt) | Students reference their gantt chart/project management software and clearly lay out their goals for the next week, assigning a champion to each one. | Student’s are vague or don’t reference their project management system. | Student’s are extremely vague in discussing goals and do not assign champions to each one. | 5 | 1 |
| Advisor Meeting Notes (5pt) | Students have taken notes during their weekly meeting with their advisor and those notes are clear and detailed. | There are notes, but they are vague. | No notes or otherwise insufficient. | 5 | 1 |
| Discretionary (5pt) | These are points are for any other aspect of the report that the advisor would like to comment on. This is at the discretion of the advisor. |  |  |  |  |

40points