## DURING DESIGNATED WORK TIME
DURING DESIGNATED WORK TIME
Date | Name | Time Started | Time Ended | Total Time Spent (H:MM) | Task Description | Completion
2025-08-28 | Demetrius Schank | 13:00 | 14:15 | 1:15 | Finished seeting up Temp Timesheet functionality, continued working on Team contract specifics (reworded mandatory, nonmandatory, and communcation expectations) . Finished temporary team contract draft and submitted. | N/A | Demetrius Total Until 10/25 | 45918.7278
2025-09-02 | Demetrius Schank | 13:00 | 14:15 | 1:15 | Sent team contract and first email to Dr. Wynne detailing meeting time requests, semester goals, project document sharing requests, etc. Started organizing TPS in our documentation. Updated TSP to mach information on our timesheets. Started working on the 'Barriers to this project' section of the TPS. | 100% (email); 55% TPS
2025-09-04 | Demetrius Schank | 13:00 | 14:15 | 1:15 | advisor meeting 1:00-1:40; resubmitted finalized Team Contract, reached out to last years group for access to their files since we have not yet gotten that. Finished TPS.
2025-09-09 | Demetrius Schank | 13:00 | 14:15 | 1:15 | Worked on contacting previous year's Cell imaging group on getting their files. Messaged graduate studnet J Fu to see if he had access to files and the video source they had. Laptop had stopped working at this point, so progress was slow for me on this day. | 50%
2025-09-11 | Demetrius Schank | 13:00 | 14:15 | 1:15 | Meeting with Dr. Wynne, set up a guideline for 4 week plan described in advisor meeting notes. Emailed ALL Cell imaging 2025 teams after being given their alternate email addresses, incase users are not active on their villanova email account. This was regarding our request to compile the previous years project and Nick F's project so Dr. Wynne and J Fu has access to personal backup. | 85%
2025-09-16 | Demetrius Schank | 13:00 | 14:15 | 45918 | Looked for additional video content publications regarding red blood cells through capillaries. Nothing concrete found, but looking through articles and their references for video sources. Signed up for Dr. K meeting for midterm prep. | 15%
2025-09-18 | Demetrius Schank | 13:00 | 14:15 | 1:15
2025-09-23 | Demetrius Schank | 13:00 | 14:15 | 1:15 | Reviewed and tested code written by jonathan, suggested some possible improvements to make. Searched more for supplemental video metadata/began formatting the already existing data. | 30%
2025-09-25 | Demetrius Schank | 13:00 | 14:10 | 1:10 | Meeting with Dr. Wynne, demonstrating code and going over which specific modifications. This includes going over the frame-rate/time problem, reported vs. playback resolution issue, and pixel to irl measurement issue. Worked a little bit more on gathering necessary metadata for our project for the "c3lc50427a.wmv" video. Had midterm demo meeting with Dr. Klein. Discussed plans to finish TPS 5, instituting a flexible deadline of 8pm on the 25th to finish tps descriptions. Briefly discussed goals for next week during the Dr. Klein meetings, which, broadly, is to get everyone up to speed on how our code works for our midterm presentation in two weeks. | 55%
2025-09-30 | Demetrius Schank | 13:00 | 14:18 | 1:18 | Reviewed W5 (A6) TPS report, going over this week's goals and upcoming problems regarding the Midterm Demo. Began working on personalized annotations for the code in document found in 'Midterm Notes and Prep' Folder in our OneDrive. In a file called 'Demetrius Midterm Demo Code Notes.docx'. | 50%
2025-10-02 | Demetrius Schank | 12:35 | 14:15 | 1:40 | Began looking for a viable 'engineering standard' for this project, starting by looking at our proposal from last semester to find what was used as our 'standard'. Although that standard worked for the purposes of the project at that point, our project has been greatly tailored since then. We now need to find an engineering standard for cell imaging analysis, not cell imaging standards themselves. Based on research from this year, this will be difficult, as there very well might not be an 'engineering standard' for cell imaging analysis. We may need to find an engineering standard for image process analysis of microscopic objects in general. At 1pm, had weekly meeting with Dr. Wynne. At ~1:30, began work on my section of TPS report. | 20% - standard 40% TPS
2025-10-07 | Demetrius Schank | 12:35 | 14:10 | 1:35 | Completed Notes on Code, Midterm Prep | 100%, 25%
2025-10-09 | Demetrius Schank | 13:00 | 14:15 | 1:15 | Midterm Prep | 90%
2025-10-21 | Demetrius Schank | 13:00 | 14:15 | 1:15 | Worked on A17 - Testing Plan | 15%
2025-10-23 | Demetrius Schank | 13:30 | 14:00 | 0:30 | Meeting with Dr. Wynne | 100%
| John Ahn | 13:00 | 14:15 | 1:15 | Completed team contract (draft) (same as groupmates^) | N/A
| John Ahn | 13:00 | 14:15 | 1:15 | Updated Gantt Chart Completed Outlook Calendar Updated OneNote
| John Ahn | 13:00 | 14:15 | 1:15 | took notes during advisor meeting, completed TPS
| Jonathan Kim | 13:00 | 14:15 | 1:15 | Finished working on Team Contract draft. Emailed to Dr. Wynne about signing the Team Contract. Worked on Solution Summary | N/A
| Jonathan Kim | 13:00 | 14:15 | 1:15 | Started research into AI. Useful things to investigate include YOLO (a type of convolutional neural network or CNN) and OpenCV. Related terms: computer vision and template matching. LLMs like ChatGPT are not recommended for this type of task.
| Jonathan Kim | 13:00 | 14:15 | 1:15 | advisor meeting 1:00-1:40, looked over previous group's files, working on TPS
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00

## OUTSIDE DESIGNATED WORK TIME
OUTSIDE DESIGNATED WORK TIME
Date | Name | Time Started | Time Ended | Total Time Spent (H:MM) | Task Description | Completion
2025-08-28 | Demetrius Schank | 10:45 | 11:25 | 0:40 | Starting setting up temp timesheet tables, continued working on Team contract. | N/A | Outside Total Until 10/25 | 14:03
|  | 17:30 | 19:00 | 1:30 | Worked more on team contract. | N/A
|  | 19:15 | 20:02 | 0:47 | Worked more on team contract, sent message in teams. | N/A | demetrius extra | need to add 1:15 due to one time sheet not reported. Estimating 4 hours for extra add on project at the end (conservative estimate)
2025-09-01 | Demetrius Schank | 21:37 | 22:46 | 1:09 | Worked more on team contract. Created a new Gantt Chart document to be updated. Note: no official response from team since 8/28, John sent CATME reminder in iMessage 8/29 but not on Teams. | N/A
2025-09-04 | Demetrius Schank | 17:15 | 17:35 | 0:20 | Finished TPS report and submitted | 100%
2025-09-18 | Demetrius Schank | 12:40 | 12:55 | 0:15 | Looked for more video material of red blood cells.
|  | 6:55 | 7:20 | 0:25 | Finsihed TPS #4 | 100%
2025-09-25 | Demetrius Schank | 10:50 | 11:35 | 0:45 | Searched for more video metadata and experiement metadata for the primary video source we are using (c3lc50427a.wmv). | 40%
|  | 12:40 | 12:55 | 0:15 | continued formatting metadata for our records. For video (c3lc50427a.wmv). | 45%
|  | 16:50 | 18:00 | 1:10 | Worked on my portion of the TSP report. Finished fathering metadata for the video. Email advisor wynne to schedule midterm demo. | 65%
|  | 21:45 | 23:57 | 2:12 | Finished TPS report. Specified more of our next week goals, future goals, and accomplishments to include details of when and where deliverables will finished. Touched up all categories of the progress report besides member timesheets and advisor notes. | 100%
2025-09-29 | Demetrius Schank | 11:59 | 12:03 | 0:04 | Emailed Dr. Klein regarding Midterm Demo scheduling conflict. | 100%
2025-10-02 | Demetrius Schank | 19:24 | 20:40 | 1:16 | Finished TPS report for W6, A5. | 100%
2025-10-07 | Demetrius Schank | 9:38 | 10:50 | 1:12 | Worked on notes regarding coding. | 85%
2025-10-09 | Demetrius Schank | 10:58 | 11:28 | 0:30 | Worked on Midterm Prep | 50%
|  | 15:00 | 15:45 | 0:45 | Midterm Prep, Midterm Demo | 100%
|  | 18:15 | 18:30 | 0:15 | Finished my portion of TPS 6 for W7. | 100%
2025-10-23 | Demetrius Schank | 16:57 | 17:30 | 0:33 | Finsihed TPS #7 W9.
2025-09-04 |  |  |  | 0:00
2025-09-04 |  |  |  | 0:00
2025-09-04 |  |  |  | 0:00
2025-09-04 |  |  |  | 0:00
2025-09-04 |  |  |  | 0:00
2025-09-04 |  |  |  | 0:00
2025-09-04 |  |  |  | 0:00
2025-09-04 |  |  |  | 0:00
2025-09-04 |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00
#NUM! |  |  |  | 0:00